## Project Plan Details
Capping 2018 Project Plan
Week | Date | Milestone | Tasks | Status | Responsible | Notes
1 | 2018-08-29 | Class 1 | Determine team roles; select project; determine project goals & requirements; define ways of communication | Completed | All | Ian, Brandon, Nick - CS; Nicole - IT; Kevin - IS | Completed
2 | 2018-09-04 | Team Meeting 1 | Create GitHub repo; begin UML and project plan; gather requirements | Completed | All | Planned to have ER diagram draft completed by 9/12 | In Progress
2 | 2018-09-05 | Class 2 | Continue gathering requirements; ask prof. questions; work on UML; begin IT setup; finalize dev. roles & approach | Completed | All | Print service API determined: Pwinty | Issue being worked
| 2018-09-07 | Team Meeting 2 | Determine weekly meeting time; work on HW 1 &2; review discussions from previous class; | Completed | All | HW to be completed, VM environment to be set up, Ian & Kevin do ER diagram, Brandon & Nick figure out APIs
3 | 2018-09-12 | Class 3 | Breakout sessions |  | All |  | At Risk
|  | HW 1 Due | Completed UML diagram and project plan, user and client requirements gathered | Completed | All
|  | Decide which API we use | Determine which API we are going to use for the actual image stylizing (w/approval from prof) | In Progress | CS
4 | 2018-09-19 | Class 4 | Project Management and Design Tooling w/Algozzine |  | All
|  | HW 2 Due | Completed ER diagram with supporting documentation; List of IT requirements | In Progress | IS/IT
5 | 2018-09-26 | Class 5 | DB Design w/Alan? |  | All
|  | UI mockup/ wireframes | Have a mockup of our UI layout and design, receive approval for any frameworks |  | IS/CS
6 | 2018-10-03 | Class 6 | Group work in class |  | All
|  | Database Due | Have a functional DB system prototype, including ER diagram and documentation, can query data live |  | All
7 | 2018-10-10 | Class 7 | Group work in class |  | All
8 | 2018-10-17 | Class 8 | Group work in class |  | All
|  | Have something running | Have something that runs |  | All
9 | 2018-10-24 | Class 9 | Group work in class |  | All
10 | 2018-10-31 | Class 10 | Group work in class |  | All
11 | 2018-11-07 | Class 11 | Group work in class |  | All
|  | Draft Presentation Due | Complete project prototype first-pass; demo ready |  | All
12 | 2018-11-14 | Class 12 | Group work in class |  | All
| 2018-11-21 | Have final deliverable complete | 99% complete, running product, with only remaining work being bux fixes |  | All
13 | 2018-11-28 | Class 13 | Group work in class |  | All
|  | Contingency period | Deliverable should be complete, use this time to fix bugs and prepare presentation |  | All
|  | Draft Documentation | Draft of final paper/documentation |  | IS
14 | 2018-12-05 | Class 14 | Presentations |  | All
|  | Paper Due | Final documentation due |  | IS
15 | 2018-12-12 | Class 15 | Final presentation |  | All

## Communications Plan
Stakeholder | What do we need to tell them | How do we communicate with them | Frequency
Professor Rivas | Full status reports; quick updates, ask questions | iLearn; email; Wed. live classes | At least once a week in addition to every Wed. in class
This class of students (CMPT475) | Quick updates; questions | Wed. live class discussions; Q&A sessions in class | Every Wed.
IT and Joint Study students who control the current test equipment | Questions on equipment availability and testing schedules | Email and in-person | Weekly
Team members | Status reports, team responsibilities | Email, phone, in-person | Daily, during in-class meetings